## Product Backlog
Product Backlog
|  |  | Organization | LBS College of Engineering
|  |  | Project | Student Performance Analysis Using Machine Learning
|  |  | Scrum Master | Abhishek Ballullaya K
|  |  | Product Owner | CS and IT Department
| Story ID | Category | Title | User Stories | Value | Sprint
| 1 | Data Preparation | Merging CSV Files | Fixing missing grades populated from previous rows | TRUE | 1
| 2 | Data Preparation | Merging CSV Files | Eligible students marked FE (FAILED FOR ELIGIBILITY) grade | TRUE | 1
| 3 | Data Pre-processing | Normalize | Normalizing Internal marks for 2019 and 2015 schemes. | FALSE | 2
| 4 | Data-Pre-processing | Normalize | Removing withheld,TBP,absent rows | FALSE | 2
| 5 | Data preprocessing | Normalize | Change grades to same scale in both 2015 and 2019 scheme | FALSE | 2
| 6 | Data Taining | Generating Models | Preparing model based on various classification algorithms | FALSE | 3
| 7 | Data Testing | Selecting Model | Selecting the best model based on accuracy | FALSE | 4
| 8 | Implementation | production | integrating the model into Department Management System web app | FALSE | 5

## Sprint 1
Sprint #1Tracking Sheet
|  | Project | Department Management System
|  | Sprint # | 1 |  | Start date |  |  | 2023-02-17
|  | Sprint focus | Data Preparation
Remaining units
|  |  |  | week 1 | [6 empty] | week 2
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Task ID | Story ID | Description | Initial estimate | 2023-02-17 | 2023-02-18 | 2023-02-19 | 2023-02-20 | 2023-02-21 | 2023-02-22 | 2023-02-23 | 2023-02-24 | 2023-02-25 | 2023-02-26 | 2023-02-27 | 2023-02-28 | 2023-03-01 | 2023-03-02
1 | 1 | Fixing missing grades populated from previous rows | 5 | 2023-02-17: 1; 2023-02-18: 1; 2023-02-21: 2; 2023-02-23: 1
2 | 1 | Discussion on further tasks | 2 | bar: 2023-02-20 to 2023-02-21
3 | 2 | Figuring out and fixing issues related to FE | 6 | 2023-02-20: 1; 2023-02-24: 1; 2023-02-25: 1; 2023-02-27: 1; 2023-02-28: 2
4 | 2 | Discussion with guide on grade variation issue in different scheme | 1 | bar: 2023-02-25
|  | Remaining units (actual) | 9 | 9 | 9 | 9 | 2 | 1 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 1 | 1
|  | Remaining units (ideal) |  | 8.1 | 7.2 | 6.3 | 5.4 | 4.5 | 3.6 | 2.7 | 1.8 | 0.9 | 0 | -0.9 | -1.8 | -2.7 | -3.6
|  | Velocity |  | 0 | 0 | 0 | 7 | 1 | 7 | 0 | 1 | -1 | 0 | 1 | -1 | 0 | 0
[14 empty] | 0 |  |  | 9
[14 empty] | 10 |  |  | 0

## Sprint 2
Sprint #2Tracking Sheet
|  | Project | Department Management System
|  | Sprint # | 2 |  | Start date |  |  | 2023-03-03
|  | Sprint focus | Data Pre-processing
Remaining units
|  |  |  | week 1 | [6 empty] | week 2
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Task ID | Story ID | Description | Initial estimate | 2023-03-03 | 2023-03-04 | 2023-03-05 | 2023-03-06 | 2023-03-07 | 2023-03-08 | 2023-03-09 | 2023-03-10 | 2023-03-11 | 2023-03-12 | 2023-03-13 | 2023-03-14 | 2023-03-15 | 2023-03-16
1 | 3 | Normalizing Internal marks for 2019 and 2015 schemes. | 5 | bar: 2023-03-03; 2023-03-05
2 | 4 | Removing withheld,TBP,absent rows | 3 | bar: 2023-03-03 to 2023-03-04
3 | 5 | Change grades to same scale in both 2015 and 2019 scheme | 4
|  | Remaining units (actual) | 7 | bar: 2023-03-03 to 2023-03-16
|  | Remaining units (ideal) |  | 6.3 | 5.6 | 4.9 | 4.2 | 3.5 | 2.8 | 2.1 | 1.4 | 0.7 | 0 | -0.7 | -1.4 | -2.1 | -2.8
|  | Velocity |  | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[15 empty] | 0 |  | 7
[15 empty] | 10 |  | 0

## Sprint 3
Sprint #3Tracking Sheet
|  | Project | Department Management System
|  | Sprint # | 3 |  | Start date |  | 2023-03-17
|  | Sprint focus | Data Training
Remaining units
|  |  |  | week 1 | [6 empty] | week 2
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Task ID | Story ID | Description | Initial estimate | 2023-03-17 | 2023-03-18 | 2023-03-19 | 2023-03-20 | 2023-03-21 | 2023-03-22 | 2023-03-23 | 2023-03-24 | 2023-03-25 | 2023-03-26 | 2023-03-27 | 2023-03-28 | 2023-03-29 | 2023-03-30
1 | 6 | familiarizing model | 4
2 | 6 | familiarizing model | 4
3 | 6 | Preparing model based on various classification algorithms | 5
4 | 6 | Preparing model based on various classification algorithms | 5
|  | Remaining units (actual) | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14
|  | Remaining units (ideal) |  | 12.6 | 11.2 | 9.8 | 8.4 | 7 | 5.6 | 4.2 | 2.8 | 1.4 | 0 | -1.4 | -2.8 | -4.2 | -5.6
|  | Velocity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[15 empty] | 0 |  | 14
[15 empty] | 10 |  | 0

## Sprint 4
Sprint #4Tracking Sheet
|  | Project | Department Management System
|  | Sprint # | 4 |  | Start date |  |  | 2023-03-31
|  | Sprint focus | Data Testing
Remaining units
|  |  |  | week 1 | [6 empty] | week 2
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Task ID | Story ID | Description | Initial estimate | 2023-03-31 | 2023-04-01 | 2023-04-02 | 2023-04-03 | 2023-04-04 | 2023-04-05 | 2023-04-06 | 2023-04-07 | 2023-04-08 | 2023-04-09 | 2023-04-10 | 2023-04-11 | 2023-04-12 | 2023-04-13
1 | 7 | Selecting the best model based on accuracy | 8
2 | 7 | Selecting the best model based on accuracy | 8
3 | 7 | further testing and choosing best | 4
|  | Remaining units (actual) | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
|  | Remaining units (ideal) |  | 10.8 | 9.6 | 8.4 | 7.2 | 6 | 4.8 | 3.6 | 2.4 | 1.2 | 0 | -1.2 | -2.4 | -3.6 | -4.8
|  | Velocity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 |  |  | 12
[14 empty] | 10 |  |  | 0

## Sprint 5
Sprint #5Tracking Sheet
|  | Project | Department Management System
|  | Sprint # | 5 |  | Start date |  |  | 2023-04-14
|  | Sprint focus | Implementation
Remaining units
|  |  |  | week 1 |  |  |  |  | week 2
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Task ID | Story ID | Description | Initial estimate | 2023-04-14 | 2023-04-15 | 2023-04-16 | 2023-04-17 | 2023-04-18 | 2023-04-19 | 2023-04-20 | 2023-04-21 | 2023-04-22 | 2023-04-23 | 2023-04-24 | 2023-04-25 | 2023-04-26 | 2023-04-27
1 | 8 | Making DMS webapp combatible for adapting the model | 5
2 | 8 | Deploying in cloud and testing | 5
3 | 8 | Internal testing in the department | 4
|  | Remaining units (actual) | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9
|  | Remaining units (ideal) |  | 8.1 | 7.2 | 6.3 | 5.4 | 4.5 | 3.6 | 2.7 | 1.8 | 0.9 | 0 | -0.9 | -1.8 | -2.7 | -3.6
|  | Velocity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 |  |  |  | 9
[13 empty] | 10 |  |  |  | 0

## README
Scrum Excel Helper Workbook
What is this? | This workbook is meant to help you manage your scrum project, as a scrum master. It can help you keep track of the product backlog, sprint backlogs, and displays the burndown chart for each sprint. (If you don't know what all those mean, read the next point.) I've kept it very basic so that you can easily extend it to suit your needs. If you have any suggestion for improvement or other coment I'd like to hear from you.
Where can I learn more about Scrum? | Scrum in 5 minutes (PDF) from softhouse
Scrum Cheat Sheet (PDF) from agile42
How do I use it? | Before project start: the product owner is responsible for managing the product backlog. Enter all user stories, with the associated priority, in the "Product backlog" sheet. Don't fill the "Sprint" column yet
Before each sprint: after you have conducted a sprint planing meeting, fill the "Sprint #" column of the product backlog to reflect which user stories will be addressed in this sprint. Copy the previous Spring sheet into a new sheet. Break down the user stories into tasks and assign them an initial estimate in scrum units.
After each work day: fill in the actual remaining scrum units for each of this sprint's task. Check the burndown chart.
Notes | Cells than you can edit use a blue background.
Sprints are assumed to be 2 weeks long (10 working days), excluding weekends; if it is not the case you'll have to adjust the Sprint sheets accordingly.
Some cells (like this one) have comments (little red triangle at the top right corner). Read them!
Origins | This work is inspired by the Scrum Template published by Nicolas Martignole on his "Touilleur Express" blog. It incorporates the following main changes:
- no need to have a separate system sheet, Spring sheets are self-contained
- remaining units computation was fixed (should reflect the situation at the end of the day)
#ERROR!
Author | Olivier Gérardin
Technical director and Java architect
E-mail me: olivier@gerardin.info
My blog: blog.gerardin.info
Licence | This work is licensed under a Creative Commons Attribution-Share Alike 3.0 Unported License.